## Sheet1
From Conf Call Oct 25
1. RiverSpring wants a clean set of web applications with no “baggage” carried forward from 6N
2. KISS, no use of excess infrastructure for AWS/Azure deployment.
3. RiverSpring to determine if dedicated web and DB servers or consolidate on one server; no impact on Fred either way.
| 4. Re Census Tracing: David to check on filtering criteria; is inbed= “No” or the presence of a Reason or Comment | error when blank or NO without reason.
5. On Nov. 5 Christina and Fred will work on the changeover from 6N to MyDatato allow the existing web applications to continue to function.
6. Minor bug on “Inbed Editor” page refresh does not blank out reason/comment when InBed=YES, Fred will fix
7. The solution will use a “bridge” database to make accessing MyData tables cleaner
8. Next week as a low priority task Fred and Christina will try to better define the new requirements previously discussed.
9. RiverSpring will install an IIS web server on the desired system and work with Fred to configure it to work with his framework.
10. There is very little CPU or I/O loading of this system, although disk storage may grow.
11. Add a “Totals” column to the daily census tracking report summary at the bottom of the page.
new issues identified
modify dev table to exactly match PositiveCensusReport